## README
SentinelPay: cost, earned value and ROI model
Currency: US dollars. All amounts are ASSUMPTIONS for planning, not quotes. Replace them with your real rates and prices.
Blue text on the Assumptions, Labor and EVM sheets = inputs you edit. Yellow fill = the key levers. Black = formulas. Green = links to other sheets.
Assumptions: every rate, price and volume lives there. Change a cell and every sheet recalculates.
Labor: monthly loaded rate per role and FTE per month for the 6-month build.
Budget: monthly cost baseline, contingency, management reserve, and cumulative Planned Value (PV).
EVM: enter % complete and actual cost each month; CPI, SPI, EAC, ETC, VAC and TCPI calculate. Months 1-3 hold ILLUSTRATIVE numbers; overwrite them.
ROI: 36-month cash model (6 months build, then selling). Summary: payback month, NPV, IRR, ROI.
Adoption factor (Assumptions B23) scales customer wins: 1.0 = base case, 0.5 = half as many customers.
Customer volumes and prices are placeholders. Do not present the ROI as a forecast until you validate them with real buyers.

## Summary
Investment and return summary
Measure | Value | How to read it
Build investment incl. reserve ($) | 738333.75 | Cash spent in the 6-month program
Cost baseline BAC ($) | 703175 | Used for earned value
First month with positive net cash | 10 | Month the product first earns more than it costs to run
Payback month (cumulative cash turns positive) | 18 | Month counted from project start; go-live is month 6
Months of selling needed to pay back | 12 | Payback month minus go-live month
Peak funding need ($) | 833504.1808 | Most cash you must fund before it turns
Net cash at month 36 ($) | 8457623.8341 | Cumulative
ROI over 36 months | 1146% | Net cash at month 36 divided by build investment
NPV at discount rate ($) | 6350335.5924 | Discount rate on Assumptions B5
IRR (annualised) | 279.3% | From monthly cash flows
Active customers at month 36 | 62.7976 | After churn
Annual recurring revenue at month 36 ($) | 9419640.9817 | Active customers x annual subscription
Adoption sensitivity (SNAPSHOT of values at build time; change Assumptions B23 to re-run live)
Adoption factor | Payback month | Net cash month 36 ($) | NPV ($) | Peak funding need ($) | Customers month 36
1 | 18 | 8457624 | 6350336 | 833504 | 62.8
0.5 | 27 | 2409645 | 1627651 | 1074077 | 31.4
0.25 | Not within 36 months | -614344 | -733691 | 1449722 | 15.7

## Assumptions
Assumptions (edit blue cells)
Item | Value | Note
Contingency (% of subtotal) | 10% | Known-unknowns; inside the cost baseline
Management reserve (% of baseline) | 5% | Unknown-unknowns; held outside the baseline, released by the sponsor
Discount rate (annual) | 12% | Assumed cost of capital
Cloud dev/test per month ($) | 3000 | Azure + AWS standby test environments
Tooling and licences per month ($) | 2000 | CI, scanners, observability
Penetration test, one-off in month 5 ($) | 25000 | Independent vendor
Compliance audit preparation, month 5 ($) | 30000 | PCI DSS / privacy readiness assessment
Legal and privacy review, month 2 ($) | 10000 | DPIA, contracts, data-processing terms
Documentation and training, month 6 ($) | 8000 | Customer docs, admin training
Annual subscription per customer ($) | 150000 | PLACEHOLDER price: validate with buyers
Onboarding fee per customer ($, one-off) | 60000 | PLACEHOLDER: integration and go-live support
Run cost per customer per month ($) | 2500 | Cloud, support share, gateway fees not passed through
Sustain team per month after go-live ($) | 70000 | Engineering, support, SRE after month 6
Sales and marketing per month from month 5 ($) | 25000 | Pre-launch ramp
New customers per month, months 7-12 | 1 | Base case before adoption factor
New customers per month, months 13-24 | 2 | Base case
New customers per month, months 25-36 | 3 | Base case
Annual customer churn | 5% | Assumed
Monthly churn (calculated) | 0.4265% | Derived from annual churn
Go-live month | 6 | End of the 6-month program
Adoption factor | 1 | Scales customer wins. 1.0 = base, 0.5 = pessimistic

## Labor
Labor plan: FTE per month (edit blue cells)
Role | Loaded rate $/month | M1 | M2 | M3 | M4 | M5 | M6 | FTE-months | Cost ($)
Program manager | 9000 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 54000
Principal architect | 14000 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 5 | 70000
Backend engineers (.NET) | 8000 | 2 | 3 | 3 | 3 | 2 | 2 | 15 | 120000
Flutter engineers | 7500 | 1 | 2 | 2 | 2 | 2 | 1 | 10 | 75000
AI / agent engineer | 10000 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 4.5 | 45000
QA / SDET | 6000 | 0.5 | 1 | 2 | 2 | 2 | 2 | 9.5 | 57000
DevOps / SRE | 9000 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 54000
Security and compliance | 10000 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 3.5 | 35000
UX and accessibility | 7000 | 0.5 | 1 | 0.5 | 1 | 0.5 | 0.25 | 3.75 | 26250
Total |  | 8 | 11 | 12 | 12.5 | 11 | 8.75 | 63.25 | 536250
Labor cost by month ($) |  | 72000 | 94000 | 101500 | 105000 | 91500 | 72250 |  | 536250
Rates are assumed loaded costs (salary, overhead). Replace with your own. Check: J13 should equal J14.

## Budget
Cost baseline and Planned Value ($)
Line | M1 | M2 | M3 | M4 | M5 | M6 | Total
Labor | 72000 | 94000 | 101500 | 105000 | 91500 | 72250 | 536250
Cloud dev/test | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 18000
Tooling and licences | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 12000
Legal and privacy review | 0 | 10000 | 0 | 0 | 0 | 0 | 10000
Penetration test | 0 | 0 | 0 | 0 | 25000 | 0 | 25000
Compliance audit prep | 0 | 0 | 0 | 0 | 30000 | 0 | 30000
Documentation and training | 0 | 0 | 0 | 0 | 0 | 8000 | 8000
Subtotal | 77000 | 109000 | 106500 | 110000 | 151500 | 85250 | 639250
Contingency | 7700 | 10900 | 10650 | 11000 | 15150 | 8525 | 63925
Monthly baseline (PV, monthly) | 84700 | 119900 | 117150 | 121000 | 166650 | 93775 | 703175
Cumulative PV | 84700 | 204600 | 321750 | 442750 | 609400 | 703175
Management reserve | 4235 | 5995 | 5857.5 | 6050 | 8332.5 | 4688.75 | 35158.75
Total funding incl. reserve | 88935 | 125895 | 123007.5 | 127050 | 174982.5 | 98463.75 | 738333.75
BAC (Budget At Completion) = H13 | [6 empty] | 703175
Management reserve is held outside BAC and is not used in EVM.

## EVM
Earned value tracker (enter blue cells monthly)
Months 1-3 below are ILLUSTRATIVE numbers to show the formulas working. Overwrite with real % complete and actual cost.
Month | PV (cum) | % complete (cum) | EV (cum) | AC (cum) | CV = EV-AC | SV = EV-PV | CPI | SPI | EAC = BAC/CPI | ETC | VAC = BAC-EAC | TCPI
M1 | 84700 | 11.8% | 82974.65 | 86400 | -3425.35 | -1725.35 | 0.96035 | 0.97963 | 732203.3898 | 645803.3898 | -29028.3898 | 1.0056
M2 | 204600 | 28.5% | 200404.875 | 208700 | -8295.125 | -4195.125 | 0.96025 | 0.9795 | 732280.7018 | 523580.7018 | -29105.7018 | 1.0168
M3 | 321750 | 44.8% | 315022.4 | 328200 | -13177.6 | -6727.6 | 0.95985 | 0.97909 | 732589.2857 | 404389.2857 | -29414.2857 | 1.0351
M4 | 442750
M5 | 609400
M6 | 703175
Reading the numbers
CPI below 1.00 = over budget for the work done. SPI below 1.00 = behind schedule.
EAC = BAC / CPI assumes today's cost efficiency continues. VAC negative = forecast overrun.
TCPI above 1.10 means the remaining work must be done much more efficiently than so far: escalate.
Thresholds used in the project plan: amber below 0.95, red below 0.90 for CPI or SPI.

## ROI
36-month cash model
Month | Phase | New customers | Active customers | Subscription revenue | Onboarding revenue | Total revenue | Build cost | Customer run cost | Sustain team | Sales and marketing | Total cost | Net cash | Cumulative net cash | Discount factor | Discounted net | Payback flag | Positive-month flag
1 | Build | 0 | 0 | 0 | 0 | 0 | 88935 | 0 | 0 | 0 | 88935 | -88935 | -88935 | 0.9906 | -88099.0464
2 | Build | 0 | 0 | 0 | 0 | 0 | 125895 | 0 | 0 | 0 | 125895 | -125895 | -214830 | 0.98129 | -123539.3973
3 | Build | 0 | 0 | 0 | 0 | 0 | 123007.5 | 0 | 0 | 0 | 123007.5 | -123007.5 | -337837.5 | 0.97207 | -119571.3373
4 | Build | 0 | 0 | 0 | 0 | 0 | 127050 | 0 | 0 | 0 | 127050 | -127050 | -464887.5 | 0.96293 | -122340.0523
5 | Build | 0 | 0 | 0 | 0 | 0 | 174982.5 | 0 | 0 | 25000 | 199982.5 | -199982.5 | -664870 | 0.95388 | -190758.757
6 | Build | 0 | 0 | 0 | 0 | 0 | 98463.75 | 0 | 0 | 25000 | 123463.75 | -123463.75 | -788333.75 | 0.94491 | -116662.278
7 | Selling | 1 | 1 | 12500 | 60000 | 72500 | 0 | 2500 | 70000 | 25000 | 97500 | -25000 | -813333.75 | 0.93603 | -23400.7348
8 | Selling | 1 | 1.9957 | 24946.6835 | 60000 | 84946.6835 | 0 | 4989.3367 | 70000 | 25000 | 99989.3367 | -15042.6532 | -828376.4032 | 0.92723 | -13948.0157
9 | Selling | 1 | 2.9872 | 37340.278 | 60000 | 97340.278 | 0 | 7468.0556 | 70000 | 25000 | 102468.0556 | -5127.7776 | -833504.1808 | 0.91852 | -4709.9432
10 | Selling | 1 | 3.9745 | 49681.0098 | 60000 | 109681.0098 | 0 | 9936.202 | 70000 | 25000 | 104936.202 | 4744.8078 | -828759.373 | 0.90988 | 4317.2143 |  | 10
11 | Selling | 1 | 4.9575 | 61969.1044 | 60000 | 121969.1044 | 0 | 12393.8209 | 70000 | 25000 | 107393.8209 | 14575.2835 | -814184.0895 | 0.90133 | 13137.1298 |  | 11
12 | Selling | 1 | 5.9364 | 74204.7864 | 60000 | 134204.7864 | 0 | 14840.9573 | 70000 | 25000 | 109840.9573 | 24363.8292 | -789820.2603 | 0.89286 | 21753.4189 |  | 12
13 | Selling | 2 | 7.9111 | 98888.2794 | 120000 | 218888.2794 | 0 | 19777.6559 | 70000 | 25000 | 114777.6559 | 104110.6235 | -685709.6368 | 0.88446 | 92082.1652 |  | 13
14 | Selling | 2 | 9.8773 | 123466.4893 | 120000 | 243466.4893 | 0 | 24693.2979 | 70000 | 25000 | 119693.2979 | 123773.1915 | -561936.4453 | 0.87615 | 108444.0086 |  | 14
15 | Selling | 2 | 11.8352 | 147939.8654 | 120000 | 267939.8654 | 0 | 29587.9731 | 70000 | 25000 | 124587.9731 | 143351.8923 | -418584.553 | 0.86792 | 124417.3371 |  | 15
16 | Selling | 2 | 13.7847 | 172308.8547 | 120000 | 292308.8547 | 0 | 34461.7709 | 70000 | 25000 | 129461.7709 | 162847.0838 | -255737.4693 | 0.85976 | 140009.0006 |  | 16
17 | Selling | 2 | 15.7259 | 196573.9025 | 120000 | 316573.9025 | 0 | 39314.7805 | 70000 | 25000 | 134314.7805 | 182259.122 | -73478.3472 | 0.85168 | 155225.741 |  | 17
18 | Selling | 2 | 17.6588 | 220735.4522 | 120000 | 340735.4522 | 0 | 44147.0904 | 70000 | 25000 | 139147.0904 | 201588.3617 | 128110.0145 | 0.84367 | 170074.194 | 18 | 18
19 | Selling | 2 | 19.5835 | 244793.9451 | 120000 | 364793.9451 | 0 | 48958.789 | 70000 | 25000 | 143958.789 | 220835.1561 | 348945.1706 | 0.83574 | 184560.8903 | 19 | 19
20 | Selling | 2 | 21.5 | 268749.8209 | 120000 | 388749.8209 | 0 | 53749.9642 | 70000 | 25000 | 148749.9642 | 239999.8567 | 588945.0273 | 0.82788 | 198692.2577 | 20 | 20
21 | Selling | 2 | 23.4083 | 292603.5172 | 120000 | 412603.5172 | 0 | 58520.7034 | 70000 | 25000 | 153520.7034 | 259082.8138 | 848027.8411 | 0.8201 | 212474.6221 | 21 | 21
22 | Selling | 2 | 25.3084 | 316355.47 | 120000 | 436355.47 | 0 | 63271.094 | 70000 | 25000 | 158271.094 | 278084.376 | 1126112.217 | 0.81239 | 225914.2092 | 22 | 22
23 | Selling | 2 | 27.2005 | 340006.113 | 120000 | 460006.113 | 0 | 68001.2226 | 70000 | 25000 | 163001.2226 | 297004.8904 | 1423117.1074 | 0.80476 | 239017.1463 | 23 | 23
24 | Selling | 2 | 29.0845 | 363555.8786 | 120000 | 483555.8786 | 0 | 72711.1757 | 70000 | 25000 | 167711.1757 | 315844.7029 | 1738961.8103 | 0.79719 | 251789.4634 | 24 | 24
25 | Selling | 3 | 31.9604 | 399505.1969 | 180000 | 579505.1969 | 0 | 79901.0394 | 70000 | 25000 | 174901.0394 | 404604.1575 | 2143565.9678 | 0.7897 | 319516.1347 | 25 | 25
26 | Selling | 3 | 34.8241 | 435301.1798 | 180000 | 615301.1798 | 0 | 87060.236 | 70000 | 25000 | 182060.236 | 433240.9439 | 2576806.9116 | 0.78228 | 338914.7296 | 26 | 26
27 | Selling | 3 | 37.6756 | 470944.4815 | 180000 | 650944.4815 | 0 | 94188.8963 | 70000 | 25000 | 189188.8963 | 461755.5852 | 3038562.4969 | 0.77492 | 357825.7632 | 27 | 27
28 | Selling | 3 | 40.5149 | 506435.7532 | 180000 | 686435.7532 | 0 | 101287.1506 | 70000 | 25000 | 196287.1506 | 490148.6026 | 3528711.0994 | 0.76764 | 376257.9768 | 28 | 28
29 | Selling | 3 | 43.3421 | 541775.6433 | 180000 | 721775.6433 | 0 | 108355.1287 | 70000 | 25000 | 203355.1287 | 518420.5146 | 4047131.614 | 0.76043 | 394219.9732 | 29 | 29
30 | Selling | 3 | 46.1572 | 576964.7974 | 180000 | 756964.7974 | 0 | 115392.9595 | 70000 | 25000 | 210392.9595 | 546571.838 | 4593703.452 | 0.75328 | 411720.2182 | 30 | 30
31 | Selling | 3 | 48.9603 | 612003.8587 | 180000 | 792003.8587 | 0 | 122400.7717 | 70000 | 25000 | 217400.7717 | 574603.0869 | 5168306.5389 | 0.7462 | 428767.0431 | 31 | 31
32 | Selling | 3 | 51.7515 | 646893.4671 | 180000 | 826893.4671 | 0 | 129378.6934 | 70000 | 25000 | 224378.6934 | 602514.7737 | 5770821.3126 | 0.73918 | 445368.6465 | 32 | 32
33 | Selling | 3 | 54.5307 | 681634.2603 | 180000 | 861634.2603 | 0 | 136326.8521 | 70000 | 25000 | 231326.8521 | 630307.4082 | 6401128.7208 | 0.73223 | 461533.096 | 33 | 33
34 | Selling | 3 | 57.2981 | 716226.8728 | 180000 | 896226.8728 | 0 | 143245.3746 | 70000 | 25000 | 238245.3746 | 657981.4983 | 7059110.2191 | 0.72535 | 477268.3308 | 34 | 34
35 | Selling | 3 | 60.0538 | 750671.9369 | 180000 | 930671.9369 | 0 | 150134.3874 | 70000 | 25000 | 245134.3874 | 685537.5495 | 7744647.7686 | 0.71853 | 492582.1632 | 35 | 35
36 | Selling | 3 | 62.7976 | 784970.0818 | 180000 | 964970.0818 | 0 | 156994.0164 | 70000 | 25000 | 251994.0164 | 712976.0654 | 8457623.8341 | 0.71178 | 507482.2805 | 36 | 36